## Read Me
Mobile Number Masking - Component Register
As of 2026-10-06
Item | Details
Purpose | Single register of every component of the Mobile Number Masking project: new components, existing components that change, backups, manual steps, tests, and the full production deployment list. Kept until the project completes.
As of | 2026-10-06
Source | Local git repository (branches ejjigiripraveen/v1.x.0-*), CHANGELOG.md, ROADMAP.md. Sandbox deploy IDs from sandbox gsquaregroup--prodreplic.
Status colours | Green = deployed / done / backed up Â· Yellow = built locally / pending approval Â· Grey = planned / not started Â· Orange = conditional / vendor Â· Blue = sandbox only / manual
Production list | Sheet "Prod Deployment List" is generated from "New Components" and "Existing Components" (rows needed in production) plus the production manual steps, in deploy order. Update the Prod Status column as you deploy.
Rule | Existing components are changed only after approval; original code is backed up first (sheet "Backups").
Rule | Sandbox first, then production pilot (1 SlashRTC + 1 360CTI + 1 MCube user), then everyone.

## Summary
Summary by Part
Counts are formulas over the other sheets
Part | Version | Scope | Status | New components | Existing components changed | New deployed to sandbox | Rows in prod list
Part 1 | v1.1.0 | Foundations | Deployed (Sandbox)
Part 2 | v1.2.0 | Masked phone panel (POC users) | Deployed (Sandbox)
Part 3 | v1.3.0 | Dialer adapters MCube + SlashRTC (POC) | Deployed (Sandbox)
Part 4 | v1.4.0 | Lead creation with hidden numbers | Deployed (Sandbox)
Part 5 | v1.5.0 | Mask leaking screens (5a-5d deployed, call panels deferred D1) | Deployed (Sandbox) - 5a to 5d
Part 6 | v1.6.0 | Reveal + audit cleanup | Planned
Part 7 | v1.7.0 | Free-text auto-masking | Planned
Part 8 | v1.8.0 | Find by number | Conditional
Part 9 | v1.9.0 | Opportunity, Contact, documents | Conditional
Part 10 | - | Vendor deliveries | Vendor
Part 11 | v2.0.0 | Go-live access (masking ON) | Planned
Security fix | optional | MCube Named Credential | Planned
Total

## New Components
New Components
Everything this project creates
# | Part | Version | Metadata Type | API Name | Parent / Object | What it does | Test class | Status | Sandbox Deploy ID / Record Id | Needed in Production | Notes
1 | Part 1 | v1.1.0 | Custom Metadata Type | Phone_Masking_Setting__mdt |  | Masking settings: format, reveal seconds, retention, kill switches |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
2 | Part 1 | v1.1.0 | Custom Field | Visible_Prefix_Digits__c | Phone_Masking_Setting__mdt | Digits shown at start (2) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
3 | Part 1 | v1.1.0 | Custom Field | Visible_Suffix_Digits__c | Phone_Masking_Setting__mdt | Digits shown at end (2) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
4 | Part 1 | v1.1.0 | Custom Field | Mask_Character__c | Phone_Masking_Setting__mdt | Mask character (X) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
5 | Part 1 | v1.1.0 | Custom Field | Country_Code_To_Strip__c | Phone_Masking_Setting__mdt | Country code removed (91) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
6 | Part 1 | v1.1.0 | Custom Field | Reveal_Seconds__c | Phone_Masking_Setting__mdt | Reveal duration (30) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
7 | Part 1 | v1.1.0 | Custom Field | Audit_Retention_Days__c | Phone_Masking_Setting__mdt | Audit retention (365) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
8 | Part 1 | v1.1.0 | Custom Field | Resolve_Enabled__c | Phone_Masking_Setting__mdt | Kill switch: real number lookup on/off |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
9 | Part 1 | v1.1.0 | Custom Field | Audit_Enabled__c | Phone_Masking_Setting__mdt | Audit on/off |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
10 | Part 1 | v1.1.0 | Custom Metadata Type | Masked_Phone_Field__mdt |  | Approved list of phone fields that may be dialed / revealed |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
11 | Part 1 | v1.1.0 | Custom Field | Object_API_Name__c | Masked_Phone_Field__mdt | Object, e.g. Lead |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
12 | Part 1 | v1.1.0 | Custom Field | Field_API_Name__c | Masked_Phone_Field__mdt | Field, e.g. Phone__c |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
13 | Part 1 | v1.1.0 | Custom Field | Display_Label__c | Masked_Phone_Field__mdt | Label in panel |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
14 | Part 1 | v1.1.0 | Custom Field | Sort_Order__c | Masked_Phone_Field__mdt | Display order |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
15 | Part 1 | v1.1.0 | Custom Field | Allow_Dial__c | Masked_Phone_Field__mdt | May be dialed |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
16 | Part 1 | v1.1.0 | Custom Field | Allow_Reveal__c | Masked_Phone_Field__mdt | May be revealed |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
17 | Part 1 | v1.1.0 | Custom Field | Active__c | Masked_Phone_Field__mdt | Active |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
18 | Part 1 | v1.1.0 | Custom Metadata Record | Phone_Masking_Setting.Default | Phone_Masking_Setting__mdt | Default settings record (2 / 2 / X / 91 / 30 / 365 / on / on) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
19 | Part 1 | v1.1.0 | Custom Metadata Record | Masked_Phone_Field.Lead_Phone | Masked_Phone_Field__mdt | Approves Lead.Phone__c (Primary) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
20 | Part 1 | v1.1.0 | Custom Metadata Record | Masked_Phone_Field.Lead_Secondary_Phone | Masked_Phone_Field__mdt | Approves Lead.Secondary_Phone__c (Secondary) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
21 | Part 1 | v1.1.0 | Custom Object | Phone_Access_Audit__c |  | Audit trail of every dial / reveal / search (masked number only); Private |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
22 | Part 1 | v1.1.0 | Custom Field | Action__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
23 | Part 1 | v1.1.0 | Custom Field | Outcome__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
24 | Part 1 | v1.1.0 | Custom Field | User__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
25 | Part 1 | v1.1.0 | Custom Field | Record_Id__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
26 | Part 1 | v1.1.0 | Custom Field | Object_Name__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
27 | Part 1 | v1.1.0 | Custom Field | Field_Key__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
28 | Part 1 | v1.1.0 | Custom Field | Masked_Number__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
29 | Part 1 | v1.1.0 | Custom Field | Channel__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
30 | Part 1 | v1.1.0 | Custom Field | Reason__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
31 | Part 1 | v1.1.0 | Custom Field | Message__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
32 | Part 1 | v1.1.0 | Custom Field | Event_Time__c | Phone_Access_Audit__c | Audit field |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
33 | Part 1 | v1.1.0 | List View | Phone_Access_Audit__c.All | Phone_Access_Audit__c | All audit rows |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
34 | Part 1 | v1.1.0 | Custom Tab | Phone_Access_Audit__c |  | Phone Access Audits tab |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
35 | Part 1 | v1.1.0 | Apex Class | PhoneMaskingConfig |  | Reads masking settings and approved field list | PhoneMaskingConfigTest | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes | Coverage 98.2%
36 | Part 1 | v1.1.0 | Apex Class | PhoneMaskUtil |  | Masks numbers (98XXXXXX21), also inside free text | PhoneMaskUtilTest | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes | Coverage 100%
37 | Part 1 | v1.1.0 | Apex Class | MaskedDialService |  | Secure real-number lookup for dialers; access check; audit | MaskedDialServiceTest | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes | Coverage 100%
38 | Part 1 | v1.1.0 | Apex Class | MaskedDialServiceCTI |  | Open CTI entry point (global webservice) for softphones | MaskedDialServiceCTITest | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes | Coverage 93.5%
39 | Part 1 | v1.1.0 | Apex Class (test) | PhoneTestDataFactory |  | Test class / test data factory (no SeeAllData) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
40 | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskingConfigTest |  | Test class / test data factory (no SeeAllData) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
41 | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskUtilTest |  | Test class / test data factory (no SeeAllData) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
42 | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceTest |  | Test class / test data factory (no SeeAllData) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
43 | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceCTITest |  | Test class / test data factory (no SeeAllData) |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes
44 | Part 1 | v1.1.0 | Permission Set | Phone_Access_Audit_Viewer |  | Read-only audit access + tab for admins |  | Deployed (Sandbox) | 0Afft000000LO8zCAG | Yes | Assign to admins after deploy
45 | Part 2 | v1.2.0 | Apex Class | MaskedPhonePanelController |  | Returns masked numbers only to the panel (1 query, no DML) | MaskedPhonePanelControllerTest | Deployed (Sandbox) | 0Afft000000LRq1CAG | Yes | Coverage 100%
46 | Part 2 | v1.2.0 | Apex Class (test) | MaskedPhonePanelControllerTest |  | 11 tests |  | Deployed (Sandbox) | 0Afft000000LRq1CAG | Yes
47 | Part 2 | v1.2.0 | Lightning Web Component | maskedPhonePanel |  | Masked phone panel on Lead page; optional click-to-dial (desktop) | Jest (2 files, not deployed) | Deployed (Sandbox) | 0Afft000000LRq1CAG | Yes | Jest needs Node.js locally
48 | Part 2 | v1.2.0 | Lightning Page | Sales_Lead_Record_Page_Masked_POC |  | Copy of Sales_Lead_Record_Page + masked panel; POC profile only |  | Deployed (Sandbox) | 0Afft000000LRq1CAG | Pilot only | Deleted after go-live (Part 11)
49 | Part 2 | v1.2.0 | Profile | POC Masked Rep |  | Clone of Presales outbound, 25 phone fields hidden, panel class access |  | Deployed (Sandbox) | 0Afft000000LRzhCAG | Pilot only (decide) | Cloned manually in Setup; overlay deployed
50 | Part 2 | v1.2.0 | User (data) | POC MCube Rep |  | Test user, MCube call center |  | Sandbox only | 005ft000000YFsfAAG | No
51 | Part 2 | v1.2.0 | User (data) | POC SlashRTC Rep |  | Test user, SlashRTC call center |  | Sandbox only | 005ft000000YFuHAAW | No
52 | Part 3 | v1.3.0 | Apex Class (test) | McubeMaskedClickToCallTest |  | Tests the new MCube masked click-to-dial method (mocked callout) |  | Deployed (Sandbox) | 0Afft000000LY6jCAG | Yes | New class so the existing test class stays untouched
53 | Part 3 | v1.3.0 | Apex Class (update of new) | MaskedDialService |  | Adds deferred audit (callout-safe) + field lookup from masked value | MaskedDialServiceTest | Deployed (Sandbox) | 0Afft000000LY6jCAG | Yes | Part 1 component updated
54 | Part 3 | v1.3.0 | Apex Class (update of new) | MaskedDialServiceCTI |  | Adds resolveMaskedClick (SlashRTC masked click) | MaskedDialServiceCTITest | Deployed (Sandbox) | 0Afft000000LY6jCAG | Yes | Part 1 component updated
55 | Part 3 | v1.3.0 | Apex Class (test, update) | MaskedDialServiceTest |  | +5 tests |  | Deployed (Sandbox) | 0Afft000000LY6jCAG | Yes
56 | Part 3 | v1.3.0 | Apex Class (test, update) | MaskedDialServiceCTITest |  | +3 tests |  | Deployed (Sandbox) | 0Afft000000LY6jCAG | Yes
57 | Part 3 | v1.3.0 | Profile (update of new) | POC Masked Rep |  | Add class access: MaskedDialServiceCTI (SlashRTC runApex) |  | Deployed (Sandbox) | 0Afft000000LYBZCA4 | Pilot only (decide)
58 | Part 3 | v1.3.0 | Lightning Page (update of new) | Sales_Lead_Record_Page_Masked_POC |  | Turn panel property Enable click-to-dial = true |  | Deployed (Sandbox) | 0Afft000000LYBZCA4 | Pilot only
59 | Part 3 | v1.3.0 | Lightning Message Channel | MaskedDialRequest__c |  | Fallback Option A only: panel sends {recordId, fieldKey} to adapters |  | Conditional |  | Conditional | Only if POC shows masked click-to-dial fails
60 | Part 4 | v1.4.0 | Custom Field | Phone_Entry__c | Lead | Entry field for primary number; copied to Phone__c and cleared |  | Deployed (Sandbox) | 0Afft000000Lc77CAC | Yes
61 | Part 4 | v1.4.0 | Custom Field | Secondary_Phone_Entry__c | Lead | Entry field for secondary number |  | Deployed (Sandbox) | 0Afft000000Lc77CAC | Yes
62 | Part 4 | v1.4.0 | Apex Class | LeadPhoneEntryHandler |  | Copies entry fields, locks primary after creation | LeadPhoneEntryHandlerTest | Deployed (Sandbox) | 0Afft000000Lc77CAC | Yes
63 | Part 4 | v1.4.0 | Apex Class (test) | LeadPhoneEntryHandlerTest |  | Tests incl. 200-record bulk |  | Deployed (Sandbox) | 0Afft000000Lc77CAC | Yes
64 | Part 4 | v1.4.0 | Profile (update of new) | POC Masked Rep |  | Edit access to Phone_Entry__c, Secondary_Phone_Entry__c |  | Deployed (Sandbox) | 0Afft000000LcALCA0 | Pilot only (decide) | Reps get it at go-live (Part 11)
65 | Part 4 | v1.4.0 | Lightning Page (update of new) | Sales_Lead_Record_Page_Masked_POC |  | Add Secondary_Phone_Entry__c (New secondary number) to the details |  | Deployed (Sandbox) | 0Afft000000LcALCA0 | Pilot only
66 | Part 5 | v1.5.0 | Apex Class | PhoneDisplayService |  | 5a: one rule for all screens - is this user masked? masks numbers for display; resolves a masked number back to the real one (with sharing, audited) | PhoneDisplayServiceTest | Deployed (Sandbox) 0Afft000000Lf3NCAS |  | Yes
67 | Part 5 | v1.5.0 | Apex Class (test) | PhoneDisplayServiceTest |  |  |  | Deployed (Sandbox) 0Afft000000Lf3NCAS |  | Yes
68 | Part 5 | v1.5.0 | Apex Class (update of new) | MaskedDialService |  | 5a: + logAccess (audit rows for MakeCall / G-Talk, deferred when a callout follows) | MaskedDialServiceTest | Deployed (Sandbox) 0Afft000000Lf3NCAS |  | Yes
69 | Part 5 | v1.5.0 | Custom Field | Phone_Masked__c | Lead | 5a: Formula: masked primary (call panels; later list views / reports) |  | Deployed (Sandbox) 0Afft000000Lf3NCAS |  | Yes
70 | Part 5 | v1.5.0 | Custom Field | Secondary_Phone_Masked__c | Lead | Formula: masked secondary |  | Planned |  | Yes
71 | Part 5 | v1.5.0 | Custom Field | Call_To_Masked__c | Call_Detail__c | 5b: Formula: masked call number |  | Deployed (Sandbox) 0Afft000000LfszCAC |  | Yes
72 | Part 6 | v1.6.0 | Apex Class | PhoneRevealService |  | Reveal for TL / Head / Admin: reason, 30 s, audit | PhoneRevealServiceTest | Planned |  | Yes
73 | Part 6 | v1.6.0 | Apex Class (test) | PhoneRevealServiceTest |  |  |  | Planned |  | Yes
74 | Part 6 | v1.6.0 | Custom Field | Reveal_Reason__c | Phone_Access_Audit__c | Picklist, 7 agreed reasons |  | Planned |  | Yes
75 | Part 6 | v1.6.0 | Custom Permission | Reveal_Phone_Number |  | Who may reveal |  | Planned |  | Yes
76 | Part 6 | v1.6.0 | Permission Set | Phone_Number_Reveal |  | Grants Reveal_Phone_Number to TL / Head / Admin |  | Planned |  | Yes
77 | Part 6 | v1.6.0 | Apex Class | PhoneAuditPurgeBatch |  | Nightly delete of audit rows older than 1 year (batch + schedulable) | PhoneAuditPurgeBatchTest | Planned |  | Yes | Schedule after deploy
78 | Part 6 | v1.6.0 | Apex Class (test) | PhoneAuditPurgeBatchTest |  |  |  | Planned |  | Yes
79 | Part 6 | v1.6.0 | Lightning Web Component (update) | maskedPhonePanel |  | Add Reveal button + reason picker |  | Planned |  | Yes
80 | Part 7 | v1.7.0 | Apex Class | FreeTextMaskService |  | Masks numbers typed in free text on save | FreeTextMaskServiceTest | Planned |  | Yes | Permanent masking
81 | Part 7 | v1.7.0 | Apex Class (test) | FreeTextMaskServiceTest |  |  |  | Planned |  | Yes
82 | Part 7 | v1.7.0 | Apex Trigger | FeedItemPhoneMaskTrigger | FeedItem | Masks numbers in Chatter posts | FreeTextMaskServiceTest | Planned |  | Yes
83 | Part 8 | v1.8.0 | Lightning Web Component | findByNumber |  | Search a number, masked result, audited | Jest | Conditional |  | Conditional | Only if POC shows global search breaks
84 | Part 8 | v1.8.0 | Apex Class | FindByNumberController |  | Server side of findByNumber | FindByNumberControllerTest | Conditional |  | Conditional
85 | Part 8 | v1.8.0 | Apex Class (test) | FindByNumberControllerTest |  |  |  | Conditional |  | Conditional
86 | Part 11 | v2.0.0 | Permission Set | Phone_Number_Full_Access |  | Full phone-field access for integration users |  | Planned |  | Yes | Assign to integration users
87 | Security fix | optional | Named Credential | MCube_API |  | MCube endpoint + key over HTTPS instead of hard-coded token / http |  | Planned |  | Yes (optional) | Separate approval
88 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingCallScreensTest |  | 5a: masked paths of MakeCallController and OfflineCallAppAPI (callouts mocked) |  | Deployed (Sandbox) |  | Yes | Existing test classes unchanged
89 | Part 5 | v1.5.0 | Profile (update of new) | POC Masked Rep |  | 5a: read access to Lead.Phone_Masked__c |  | Deployed (Sandbox) |  | Pilot only (decide)
90 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingHistoryTest |  | 5b: call history, History & Activity and MCube log masking (callouts mocked) |  | Deployed (Sandbox) | 0Afft000000LfszCAC | Yes
91 | Part 5 | v1.5.0 | Apex Class (update of new) | PhoneDisplayService |  | 5b: + forDisplay, historyValueForDisplay | PhoneMaskingHistoryTest | Deployed (Sandbox) | 0Afft000000LfszCAC | Yes
92 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingLeadToolsTest |  | 5c: merge lists masked; Update Contact never saves masked values, primary locked for masked users |  | Deployed (Sandbox) | 0Afft000000LkRFCA0 | Yes
93 | Part 5 | v1.5.0 | Apex Class (update of new) | PhoneDisplayService |  | 5c: + maskRecords, prepareContactInput | PhoneMaskingLeadToolsTest | Deployed (Sandbox) | 0Afft000000LkRFCA0 | Yes
94 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingPushTest |  | 5d: selection lists masked for masked users; eligibility unchanged |  | Deployed (Sandbox) | 0Afft000000Lm1dCAC | Yes

## Existing Components
Existing Components that Change
Changed only after approval; original backed up first
# | Part | Version | Metadata Type | API Name | What changes | Why | Approval | Original backup | Status | Needed in Production | Notes
1 | Part 2 | v1.2.0 | Lightning App (assignment) | Pre_Sales (Gsquare Housing) | One new page-assignment row: Lead, Pre Sales, desktop, POC Masked Rep -> masked page | Show the masked page to POC users only | Approved 2026-10-05 | Commit 1adf63f (snapshot) | Done (Sandbox, App Builder) | Pilot only (manual) | App cannot be deployed by metadata (duplicate Analytics Cloud profile names)
2 | Part 3 | v1.3.0 | Visualforce Page | mcubeSoftphoneCTIAddOn | In onClickToDial: if the click comes from the masked panel, call the new server method with recordId + fieldKey | MCube receives 98XXXXXX21, which it cannot dial | Approved 2026-10-06 | backup/v1.3.0-pre-change | Deployed (Sandbox) 0Afft000000LY6jCAG | Yes | Normal clicks unchanged
3 | Part 3 | v1.3.0 | Apex Class | McubeSoftphoneAddOnController | Add new @RemoteAction clickToCallMasked(recordId, fieldKey): resolves via MaskedDialService, then reuses clickToCallRemote | Real number resolved on the server, never in the browser | Approved 2026-10-06 | backup/v1.3.0-pre-change | Deployed (Sandbox) 0Afft000000LY6jCAG | Yes | Existing methods not edited
4 | Part 3 | v1.3.0 | Aura Component | slashPhone (slashPhoneHelper.js) | In onClickToDial listener: if masked click, runApex MaskedDialServiceCTI.resolveForDial, then continue existing flow | SlashRTC receives 98XXXXXX21 | Approved 2026-10-06 | backup/v1.3.0-pre-change | Deployed (Sandbox) 0Afft000000LY6jCAG | Yes | Number exists briefly inside the SlashRTC softphone (vendor limitation)
5 | Part 3 | v1.3.0 | Call Center | SlashRTCAdapter | Adapter URL -> sandbox index page | Sandbox adapter points to production | Manual by you (Setup) | backup/v1.3.0-pre-change | Sandbox only - manual | No | Production URL is already correct
6 | Part 3 | v1.3.0 | User (data) | POC MCube Rep | Set MobilePhone = agent number registered with MCube | MCube rings the agent on User.MobilePhone first | Pending |  | Sandbox only | No
7 | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | On form load: if the user cannot see Phone__c, show Phone (entry) + Secondary Phone (entry) inputs instead | Phone__c input disappears for masked users, so they could not create Leads | Approved 2026-10-06 | backup/v1.4.0-pre-change | Deployed (Sandbox) 0Afft000000Lc77CAC | Yes | No change for users who can see Phone__c
8 | Part 4 | v1.4.0 | Aura Component | NewRefLeadCmp | Same as NewLeadCmp (New Referral Lead quick action) | Same | Approved 2026-10-06 | backup/v1.4.0-pre-change | Deployed (Sandbox) 0Afft000000Lc77CAC | Yes
9 | Part 4 | v1.4.0 | Apex Trigger | LeadTrigger | One call at the very top (before insert / update): LeadPhoneEntryHandler copies entry fields before the existing formatting and duplicate check | Copy must run before RelatedSourceHandler.checkMobileNumber / duplicateCheck | Approved 2026-10-06 | backup/v1.4.0-pre-change | Deployed (Sandbox) 0Afft000000Lc77CAC | Yes | Existing logic untouched
10 | Part 4 | v1.4.0 | Apex Class | LeadTriggerHandler / RelatedSourceHandler | No change (existing tests re-run) | Dependency | - | backup/v1.4.0-pre-change | No change | No
11 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page | Swap phone fields for entry fields | Fields vanish for masked users | Not requested yet | backup/v1.4.0-pre-change | Planned | Yes
12 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page1_sales | Swap phone fields for entry fields | Same | Not requested yet | backup/v1.4.0-pre-change | Planned | Yes
13 | Part 5 | v1.5.0 | Aura Component | MakeCall | 5a: NO CHANGE needed - shows what readContacts returns and sends it back | Sends full numbers to the browser | - | backup/v1.5.0-part5a-pre-change | No change (5a) | No | Plus its existing test class
14 | Part 5 | v1.5.0 | Apex Class | MakeCallController | 5a: readContacts returns masked for masked users; callCustomer resolves a masked number on the server | Sends full numbers to the browser | Approved 2026-10-06 | backup/v1.5.0-part5a-pre-change | Deployed (Sandbox) 0Afft000000Lf3NCAS | Yes | Plus its existing test class
15 | Part 5 | v1.5.0 | Lightning Web Component | utilityCallComponent | 5a: NO CHANGE needed - sends the number back to triggerCall, resolved on the server | Sends full numbers to the browser | - | backup/v1.5.0-part5a-pre-change | No change (5a) | No | Plus its existing test class
16 | Part 5 | v1.5.0 | Lightning Web Component | offlineCallQuickActionCmp | 5a: NO CHANGE needed (same as utilityCallComponent) | Sends full numbers to the browser | - | backup/v1.5.0-part5a-pre-change | No change (5a) | No | Plus its existing test class
17 | Part 5 | v1.5.0 | Apex Class | OfflineCallAppAPI | 5a: getLeadPhone / getOppPhone masked for masked users; triggerCall resolves a masked number on the server | Sends full numbers to the browser | Approved 2026-10-06 | backup/v1.5.0-part5a-pre-change | Deployed (Sandbox) 0Afft000000Lf3NCAS | Yes | Plus its existing test class
18 | Part 5 | v1.5.0 | Aura Component | CallPanel | Postponed: the Aura view form has no onload event. Proposed: replace the Phone line with a new LWC maskedPhoneField | Sends full numbers to the browser | New approach pending approval | backup/v1.5.0-part5a-pre-change | Pending approval | Yes | Plus its existing test class
19 | Part 5 | v1.5.0 | Aura Component | CallPanel_Outbound | Postponed: the Aura view form has no onload event. Proposed: replace the Phone line with a new LWC maskedPhoneField | Sends full numbers to the browser | New approach pending approval | backup/v1.5.0-part5a-pre-change | Pending approval | Yes | Plus its existing test class
20 | Part 5 | v1.5.0 | Aura Component | mCubeLightningPage | 5b: NO CHANGE - shows what callRecords returns | Sends full numbers to the browser | - | backup/v1.5.0-part5b-pre-change | No change (5b) | No | Plus its existing test class
21 | Part 5 | v1.5.0 | Apex Class | LeadHistoryandActivityController | 5b: GetData masks phone history values and call numbers for masked users | Sends full numbers to the browser | Approved 2026-10-06 | backup/v1.5.0-part5b-pre-change | Deployed (Sandbox) 0Afft000000LfszCAC | Yes | Plus its existing test class
22 | Part 5 | v1.5.0 | Apex Class | mCubeController | 5b: callRecords masked for masked users; log__c Request / Response masked for everyone | Sends full numbers to the browser | Approved 2026-10-06 | backup/v1.5.0-part5b-pre-change | Deployed (Sandbox) 0Afft000000LfszCAC | Yes | Plus its existing test class
23 | Part 5 | v1.5.0 | Aura Component | LeadMergeCmp | 5c: NO CHANGE - shows what Apex returns | Sends full numbers to the browser | - | backup/v1.5.0-part5c-pre-change | No change (5c) | No | Plus its existing test class
24 | Part 5 | v1.5.0 | Apex Class | LeadMergeController | Return masked values | Sends full numbers to the browser | Approved 2026-10-07 | backup/v1.5.0-part5c-pre-change | Deployed (Sandbox) 0Afft000000LkRFCA0 | Yes | Plus its existing test class
25 | Part 5 | v1.5.0 | Aura Component | UpdateContactDetails | Primary read-only masked; secondary masked entry | Sends full numbers to the browser | Approved 2026-10-07 | backup/v1.5.0-part5c-pre-change | Deployed (Sandbox) 0Afft000000LkRFCA0 | Yes | Plus its existing test class
26 | Part 5 | v1.5.0 | Apex Class | updateContactDetails | Same | Sends full numbers to the browser | Approved 2026-10-07 | backup/v1.5.0-part5c-pre-change | Deployed (Sandbox) 0Afft000000LkRFCA0 | Yes | Plus its existing test class
27 | Part 5 | v1.5.0 | Lightning Web Component | leadBulkPush | 5d: NO CHANGE - shows what Apex returns | Sends full numbers to the browser | - | backup/v1.5.0-part5d-pre-change | No change (5d) | No | Plus its existing test class
28 | Part 5 | v1.5.0 | Apex Class | LeadBulkPushController | Return masked values | Sends full numbers to the browser | Approved 2026-10-07 | backup/v1.5.0-part5d-pre-change | Deployed (Sandbox) 0Afft000000Lm1dCAC | Yes | Plus its existing test class
29 | Part 5 | v1.5.0 | Lightning Web Component | leadYotelPush | 5d: NO CHANGE - shows what Apex returns | Sends full numbers to the browser | - | backup/v1.5.0-part5d-pre-change | No change (5d) | No | Plus its existing test class
30 | Part 5 | v1.5.0 | Apex Class | LeadYotelBulkPushController | Return masked values | Sends full numbers to the browser | Approved 2026-10-07 | backup/v1.5.0-part5d-pre-change | Deployed (Sandbox) 0Afft000000Lm1dCAC | Yes | Plus its existing test class
31 | Part 5 | v1.5.0 | Lightning Web Component | leadMsgConversationLWC | 5e: NO CHANGE - shows what Apex returns | Sends full numbers to the browser | - | backup/v1.5.0-part5e-pre-change | No change (5e) | No | Plus its existing test class
32 | Part 5 | v1.5.0 | Apex Class | LeadMsgConversationController | 5e: mask numbers in conversation message / rawJson / senderName for masked users | Sends full numbers to the browser | Pending approval | backup/v1.5.0-part5e-pre-change | Planned | Yes | Plus its existing test class
33 | Part 7 | v1.7.0 | Apex Trigger | TaskTrigger | Call FreeTextMaskService on save | Numbers typed in call notes | Not requested yet | Add to baseline first | Planned | Yes
34 | Part 7 | v1.7.0 | Apex Trigger | CallDetailTrigger | Call FreeTextMaskService on save (free-text fields only) | Numbers typed in call logs | Not requested yet | Add to baseline first | Planned | Yes | Structured number fields untouched
35 | Part 7 | v1.7.0 | Apex Trigger / Class | Opportunity + feedback object triggers (TBD) | Call FreeTextMaskService on save | Numbers typed in Opportunity / feedback text | Not requested yet | Add to baseline first | Planned | Yes | Exact names confirmed before Part 7
36 | Part 8 | v1.8.0 | Lightning Web Component | searchComponent | Possibly reuse for Find by number | Global search may stop matching hidden fields | Not requested yet | Baseline v1.0.0 | Conditional | Conditional
37 | Part 9 | v1.9.0 | Lightning Web Component | cancellationRequest | Fails completely if Opportunity Mobile__c is hidden | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
38 | Part 9 | v1.9.0 | Lightning Web Component | opportunitySummaryLWC | Masked display | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
39 | Part 9 | v1.9.0 | Lightning Web Component | registrationTeamFileUpload | Masked display | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
40 | Part 9 | v1.9.0 | Lightning Web Component | kycAndQuotationTabComponent | Masked co-applicant entry | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
41 | Part 9 | v1.9.0 | Aura Component | siteVisitFeedbackForm | Masked display | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
42 | Part 9 | v1.9.0 | Aura Component | createBookingCmp | Masked display | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
43 | Part 9 | v1.9.0 | Lightning Web Component | showConvertedOppRecord | Masked display | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
44 | Part 9 | v1.9.0 | Quick Action | Contact.Co_Applicant_1 / 2 / 3, Contact.Update_Contact_Details | Masked entry | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
45 | Part 9 | v1.9.0 | Visualforce Page | 19 customer document pages (BookingForm, letters, quotations, receipts) | Keep real number for document teams | Only if Decision 1 = hide Contact / Opportunity numbers | Waiting on Decision 1 | Baseline v1.0.0 | Conditional | Conditional
46 | Part 11 | v2.0.0 | Profile | ~40 rep profiles (Presales outbound, Sales, CRM Team, Referral Team, TLs ...) | Remove phone-field access; Export Reports / API Enabled where safe | This switches masking on | Not requested yet | Baseline v1.0.0 | Planned | Yes | The go-live switch
47 | Part 11 | v2.0.0 | Lightning Page | Lead_Record_Page | Add maskedPhonePanel (click-to-dial on) | Reps need the panel on every Lead page they use | Not requested yet | Baseline v1.0.0 | Planned | Yes
48 | Part 11 | v2.0.0 | Lightning Page | Sales_Lead_Record_Page | Add maskedPhonePanel (click-to-dial on) | Reps need the panel on every Lead page they use | Not requested yet | Baseline v1.0.0 | Planned | Yes
49 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page | Add maskedPhonePanel (click-to-dial on) | Reps need the panel on every Lead page they use | Not requested yet | Baseline v1.0.0 | Planned | Yes
50 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page1_sales | Add maskedPhonePanel (click-to-dial on) | Reps need the panel on every Lead page they use | Not requested yet | Baseline v1.0.0 | Planned | Yes
51 | Part 11 | v2.0.0 | Lightning Page | Lead_Record_Page3 | Add maskedPhonePanel (click-to-dial on) | Reps need the panel on every Lead page they use | Not requested yet | Add to baseline first | Planned | Yes
52 | Part 11 | v2.0.0 | Lightning App (assignment) | Pre_Sales (Gsquare Housing) | Remove POC assignment row | Cleanup | Not requested yet | Commit 1adf63f | Planned | Pilot cleanup
53 | Security fix | optional | Apex Class | McubeAutoDailerApi | Use Named Credential MCube_API instead of hard-coded token / http URL | Security debt | Not requested yet | Baseline v1.0.0 | Planned | Yes (optional)
54 | Security fix | optional | Apex Class | mCubeController | Use Named Credential MCube_API instead of hard-coded token / http URL | Security debt | Not requested yet | Baseline v1.0.0 | Planned | Yes (optional)
55 | Security fix | optional | Apex Class | McubeSoftphoneAddOnController | Use Named Credential MCube_API instead of hard-coded token / http URL | Security debt | Not requested yet | Baseline v1.0.0 | Planned | Yes (optional)
56 | Part 5 | v1.5.0 | Aura Component | LeadHistoryandActivityCmp | 5b: NO CHANGE - shows what GetData returns | History & Activity on 4 Lead pages | - | backup/v1.5.0-part5b-pre-change | No change (5b) | No | First backed up in 5b

## Prod Deployment List
Production Deployment List (all parts)
Deploy in this order, part by part. Change set test level: Run specified tests (classes in column I). Update "Prod Status" as you go.
Order | Part | Version | Change Set Type | API Name | Parent / Object | New / Existing | Deploy Method | Test class to run | Needed in Production | Prod Status | Notes
1 | Part 1 | v1.1.0 | Custom Metadata Type | Masked_Phone_Field__mdt |  | New | Change set |  | Yes | Not deployed
2 | Part 1 | v1.1.0 | Custom Metadata Type | Phone_Masking_Setting__mdt |  | New | Change set |  | Yes | Not deployed
3 | Part 1 | v1.1.0 | Custom Object | Phone_Access_Audit__c |  | New | Change set |  | Yes | Not deployed
4 | Part 1 | v1.1.0 | Custom Field | Action__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
5 | Part 1 | v1.1.0 | Custom Field | Active__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
6 | Part 1 | v1.1.0 | Custom Field | Allow_Dial__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
7 | Part 1 | v1.1.0 | Custom Field | Allow_Reveal__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
8 | Part 1 | v1.1.0 | Custom Field | Audit_Enabled__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
9 | Part 1 | v1.1.0 | Custom Field | Audit_Retention_Days__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
10 | Part 1 | v1.1.0 | Custom Field | Channel__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
11 | Part 1 | v1.1.0 | Custom Field | Country_Code_To_Strip__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
12 | Part 1 | v1.1.0 | Custom Field | Display_Label__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
13 | Part 1 | v1.1.0 | Custom Field | Event_Time__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
14 | Part 1 | v1.1.0 | Custom Field | Field_API_Name__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
15 | Part 1 | v1.1.0 | Custom Field | Field_Key__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
16 | Part 1 | v1.1.0 | Custom Field | Mask_Character__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
17 | Part 1 | v1.1.0 | Custom Field | Masked_Number__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
18 | Part 1 | v1.1.0 | Custom Field | Message__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
19 | Part 1 | v1.1.0 | Custom Field | Object_API_Name__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
20 | Part 1 | v1.1.0 | Custom Field | Object_Name__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
21 | Part 1 | v1.1.0 | Custom Field | Outcome__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
22 | Part 1 | v1.1.0 | Custom Field | Reason__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
23 | Part 1 | v1.1.0 | Custom Field | Record_Id__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
24 | Part 1 | v1.1.0 | Custom Field | Resolve_Enabled__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
25 | Part 1 | v1.1.0 | Custom Field | Reveal_Seconds__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
26 | Part 1 | v1.1.0 | Custom Field | Sort_Order__c | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
27 | Part 1 | v1.1.0 | Custom Field | User__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
28 | Part 1 | v1.1.0 | Custom Field | Visible_Prefix_Digits__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
29 | Part 1 | v1.1.0 | Custom Field | Visible_Suffix_Digits__c | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
30 | Part 1 | v1.1.0 | Custom Metadata Record | Masked_Phone_Field.Lead_Phone | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
31 | Part 1 | v1.1.0 | Custom Metadata Record | Masked_Phone_Field.Lead_Secondary_Phone | Masked_Phone_Field__mdt | New | Change set |  | Yes | Not deployed
32 | Part 1 | v1.1.0 | Custom Metadata Record | Phone_Masking_Setting.Default | Phone_Masking_Setting__mdt | New | Change set |  | Yes | Not deployed
33 | Part 1 | v1.1.0 | List View | Phone_Access_Audit__c.All | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
34 | Part 1 | v1.1.0 | Custom Tab | Phone_Access_Audit__c |  | New | Change set |  | Yes | Not deployed
35 | Part 1 | v1.1.0 | Apex Class | MaskedDialService |  | New | Change set | MaskedDialServiceTest | Yes | Not deployed | Coverage 100%
36 | Part 1 | v1.1.0 | Apex Class | MaskedDialServiceCTI |  | New | Change set | MaskedDialServiceCTITest | Yes | Not deployed | Coverage 93.5%
37 | Part 1 | v1.1.0 | Apex Class | PhoneMaskingConfig |  | New | Change set | PhoneMaskingConfigTest | Yes | Not deployed | Coverage 98.2%
38 | Part 1 | v1.1.0 | Apex Class | PhoneMaskUtil |  | New | Change set | PhoneMaskUtilTest | Yes | Not deployed | Coverage 100%
39 | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceCTITest |  | New | Change set |  | Yes | Not deployed
40 | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceTest |  | New | Change set |  | Yes | Not deployed
41 | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskingConfigTest |  | New | Change set |  | Yes | Not deployed
42 | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskUtilTest |  | New | Change set |  | Yes | Not deployed
43 | Part 1 | v1.1.0 | Apex Class (test) | PhoneTestDataFactory |  | New | Change set |  | Yes | Not deployed
44 | Part 1 | v1.1.0 | Permission Set | Phone_Access_Audit_Viewer |  | New | Change set |  | Yes | Not deployed | Assign to admins after deploy
45 | Part 2 | v1.2.0 | Apex Class | MaskedPhonePanelController |  | New | Change set | MaskedPhonePanelControllerTest | Yes | Not deployed | Coverage 100%
46 | Part 2 | v1.2.0 | Apex Class (test) | MaskedPhonePanelControllerTest |  | New | Change set |  | Yes | Not deployed
47 | Part 2 | v1.2.0 | Lightning Web Component | maskedPhonePanel |  | New | Change set | Jest (2 files, not deployed) | Yes | Not deployed | Jest needs Node.js locally
48 | Part 2 | v1.2.0 | Lightning Page | Sales_Lead_Record_Page_Masked_POC |  | New | Change set |  | Pilot only | Not deployed | Deleted after go-live (Part 11)
49 | Part 2 | v1.2.0 | Profile | POC Masked Rep |  | New | Change set |  | Pilot only (decide) | Not deployed | Cloned manually in Setup; overlay deployed
50 | Part 2 | v1.2.0 | Lightning App (assignment) | Pre_Sales (Gsquare Housing) |  | Existing (change) | Manual / Change set |  | Pilot only (manual) | Not deployed | One new page-assignment row: Lead, Pre Sales, desktop, POC Masked Rep -> masked page
51 | Part 3 | v1.3.0 | Lightning Message Channel | MaskedDialRequest__c |  | New | Change set |  | Conditional | Not deployed | Only if POC shows masked click-to-dial fails
52 | Part 3 | v1.3.0 | Apex Class (update of new) | MaskedDialService |  | New | Change set | MaskedDialServiceTest | Yes | Not deployed | Part 1 component updated
53 | Part 3 | v1.3.0 | Apex Class (update of new) | MaskedDialServiceCTI |  | New | Change set | MaskedDialServiceCTITest | Yes | Not deployed | Part 1 component updated
54 | Part 3 | v1.3.0 | Apex Class | McubeSoftphoneAddOnController |  | Existing (change) | Change set |  | Yes | Not deployed | Add new @RemoteAction clickToCallMasked(recordId, fieldKey): resolves via MaskedDialService, then reuses clickToCallRemote
55 | Part 3 | v1.3.0 | Apex Class (test, update) | MaskedDialServiceCTITest |  | New | Change set |  | Yes | Not deployed
56 | Part 3 | v1.3.0 | Apex Class (test, update) | MaskedDialServiceTest |  | New | Change set |  | Yes | Not deployed
57 | Part 3 | v1.3.0 | Apex Class (test) | McubeMaskedClickToCallTest |  | New | Change set |  | Yes | Not deployed | New class so the existing test class stays untouched
58 | Part 3 | v1.3.0 | Visualforce Page | mcubeSoftphoneCTIAddOn |  | Existing (change) | Change set |  | Yes | Not deployed | In onClickToDial: if the click comes from the masked panel, call the new server method with recordId + fieldKey
59 | Part 3 | v1.3.0 | Aura Component | slashPhone (slashPhoneHelper.js) |  | Existing (change) | Change set |  | Yes | Not deployed | In onClickToDial listener: if masked click, runApex MaskedDialServiceCTI.resolveForDial, then continue existing flow
60 | Part 3 | v1.3.0 | Lightning Page (update of new) | Sales_Lead_Record_Page_Masked_POC |  | New | Change set |  | Pilot only | Not deployed
61 | Part 3 | v1.3.0 | Profile (update of new) | POC Masked Rep |  | New | Change set |  | Pilot only (decide) | Not deployed
62 | Part 4 | v1.4.0 | Custom Field | Phone_Entry__c | Lead | New | Change set |  | Yes | Not deployed
63 | Part 4 | v1.4.0 | Custom Field | Secondary_Phone_Entry__c | Lead | New | Change set |  | Yes | Not deployed
64 | Part 4 | v1.4.0 | Apex Class | LeadPhoneEntryHandler |  | New | Change set | LeadPhoneEntryHandlerTest | Yes | Not deployed
65 | Part 4 | v1.4.0 | Apex Class (test) | LeadPhoneEntryHandlerTest |  | New | Change set |  | Yes | Not deployed
66 | Part 4 | v1.4.0 | Apex Trigger | LeadTrigger |  | Existing (change) | Change set |  | Yes | Not deployed | One call at the very top (before insert / update): LeadPhoneEntryHandler copies entry fields before the existing formatting and duplicate check
67 | Part 4 | v1.4.0 | Aura Component | NewLeadCmp |  | Existing (change) | Change set |  | Yes | Not deployed | On form load: if the user cannot see Phone__c, show Phone (entry) + Secondary Phone (entry) inputs instead
68 | Part 4 | v1.4.0 | Aura Component | NewRefLeadCmp |  | Existing (change) | Change set |  | Yes | Not deployed | Same as NewLeadCmp (New Referral Lead quick action)
69 | Part 4 | v1.4.0 | Lightning Page (update of new) | Sales_Lead_Record_Page_Masked_POC |  | New | Change set |  | Pilot only | Not deployed
70 | Part 4 | v1.4.0 | Profile (update of new) | POC Masked Rep |  | New | Change set |  | Pilot only (decide) | Not deployed | Reps get it at go-live (Part 11)
71 | Part 5 | v1.5.0 | Custom Field | Call_To_Masked__c | Call_Detail__c | New | Change set |  | Yes | Not deployed
72 | Part 5 | v1.5.0 | Custom Field | Phone_Masked__c | Lead | New | Change set |  | Yes | Not deployed
73 | Part 5 | v1.5.0 | Custom Field | Secondary_Phone_Masked__c | Lead | New | Change set |  | Yes | Not deployed
74 | Part 5 | v1.5.0 | Apex Class | LeadBulkPushController |  | Existing (change) | Change set |  | Yes | Not deployed | Return masked values
75 | Part 5 | v1.5.0 | Apex Class | LeadHistoryandActivityController |  | Existing (change) | Change set |  | Yes | Not deployed | 5b: GetData masks phone history values and call numbers for masked users
76 | Part 5 | v1.5.0 | Apex Class | LeadMergeController |  | Existing (change) | Change set |  | Yes | Not deployed | Return masked values
77 | Part 5 | v1.5.0 | Apex Class | LeadMsgConversationController |  | Existing (change) | Change set |  | Yes | Not deployed | 5e: mask numbers in conversation message / rawJson / senderName for masked users
78 | Part 5 | v1.5.0 | Apex Class | LeadYotelBulkPushController |  | Existing (change) | Change set |  | Yes | Not deployed | Return masked values
79 | Part 5 | v1.5.0 | Apex Class | MakeCallController |  | Existing (change) | Change set |  | Yes | Not deployed | 5a: readContacts returns masked for masked users; callCustomer resolves a masked number on the server
80 | Part 5 | v1.5.0 | Apex Class (update of new) | MaskedDialService |  | New | Change set | MaskedDialServiceTest | Yes | Not deployed
81 | Part 5 | v1.5.0 | Apex Class | mCubeController |  | Existing (change) | Change set |  | Yes | Not deployed | 5b: callRecords masked for masked users; log__c Request / Response masked for everyone
82 | Part 5 | v1.5.0 | Apex Class | OfflineCallAppAPI |  | Existing (change) | Change set |  | Yes | Not deployed | 5a: getLeadPhone / getOppPhone masked for masked users; triggerCall resolves a masked number on the server
83 | Part 5 | v1.5.0 | Apex Class (update of new) | PhoneDisplayService |  | New | Change set | PhoneMaskingHistoryTest | Yes | Not deployed
84 | Part 5 | v1.5.0 | Apex Class | PhoneDisplayService |  | New | Change set | PhoneDisplayServiceTest | Yes | Not deployed
85 | Part 5 | v1.5.0 | Apex Class (update of new) | PhoneDisplayService |  | New | Change set | PhoneMaskingLeadToolsTest | Yes | Not deployed
86 | Part 5 | v1.5.0 | Apex Class | updateContactDetails |  | Existing (change) | Change set |  | Yes | Not deployed | Same
87 | Part 5 | v1.5.0 | Apex Class (test) | PhoneDisplayServiceTest |  | New | Change set |  | Yes | Not deployed
88 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingCallScreensTest |  | New | Change set |  | Yes | Not deployed | Existing test classes unchanged
89 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingHistoryTest |  | New | Change set |  | Yes | Not deployed
90 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingLeadToolsTest |  | New | Change set |  | Yes | Not deployed
91 | Part 5 | v1.5.0 | Apex Class (test) | PhoneMaskingPushTest |  | New | Change set |  | Yes | Not deployed
92 | Part 5 | v1.5.0 | Aura Component | CallPanel |  | Existing (change) | Change set |  | Yes | Not deployed | Postponed: the Aura view form has no onload event. Proposed: replace the Phone line with a new LWC maskedPhoneField
93 | Part 5 | v1.5.0 | Aura Component | CallPanel_Outbound |  | Existing (change) | Change set |  | Yes | Not deployed | Postponed: the Aura view form has no onload event. Proposed: replace the Phone line with a new LWC maskedPhoneField
94 | Part 5 | v1.5.0 | Aura Component | UpdateContactDetails |  | Existing (change) | Change set |  | Yes | Not deployed | Primary read-only masked; secondary masked entry
95 | Part 5 | v1.5.0 | Profile (update of new) | POC Masked Rep |  | New | Change set |  | Pilot only (decide) | Not deployed
96 | Part 6 | v1.6.0 | Custom Field | Reveal_Reason__c | Phone_Access_Audit__c | New | Change set |  | Yes | Not deployed
97 | Part 6 | v1.6.0 | Custom Permission | Reveal_Phone_Number |  | New | Change set |  | Yes | Not deployed
98 | Part 6 | v1.6.0 | Apex Class | PhoneAuditPurgeBatch |  | New | Change set | PhoneAuditPurgeBatchTest | Yes | Not deployed | Schedule after deploy
99 | Part 6 | v1.6.0 | Apex Class | PhoneRevealService |  | New | Change set | PhoneRevealServiceTest | Yes | Not deployed
100 | Part 6 | v1.6.0 | Apex Class (test) | PhoneAuditPurgeBatchTest |  | New | Change set |  | Yes | Not deployed
101 | Part 6 | v1.6.0 | Apex Class (test) | PhoneRevealServiceTest |  | New | Change set |  | Yes | Not deployed
102 | Part 6 | v1.6.0 | Lightning Web Component (update) | maskedPhonePanel |  | New | Change set |  | Yes | Not deployed
103 | Part 6 | v1.6.0 | Permission Set | Phone_Number_Reveal |  | New | Change set |  | Yes | Not deployed
104 | Part 7 | v1.7.0 | Apex Class | FreeTextMaskService |  | New | Change set | FreeTextMaskServiceTest | Yes | Not deployed | Permanent masking
105 | Part 7 | v1.7.0 | Apex Class (test) | FreeTextMaskServiceTest |  | New | Change set |  | Yes | Not deployed
106 | Part 7 | v1.7.0 | Apex Trigger | CallDetailTrigger |  | Existing (change) | Change set |  | Yes | Not deployed | Call FreeTextMaskService on save (free-text fields only)
107 | Part 7 | v1.7.0 | Apex Trigger | FeedItemPhoneMaskTrigger | FeedItem | New | Change set | FreeTextMaskServiceTest | Yes | Not deployed
108 | Part 7 | v1.7.0 | Apex Trigger / Class | Opportunity + feedback object triggers (TBD) |  | Existing (change) | Change set |  | Yes | Not deployed | Call FreeTextMaskService on save
109 | Part 7 | v1.7.0 | Apex Trigger | TaskTrigger |  | Existing (change) | Change set |  | Yes | Not deployed | Call FreeTextMaskService on save
110 | Part 8 | v1.8.0 | Apex Class | FindByNumberController |  | New | Change set | FindByNumberControllerTest | Conditional | Not deployed
111 | Part 8 | v1.8.0 | Apex Class (test) | FindByNumberControllerTest |  | New | Change set |  | Conditional | Not deployed
112 | Part 8 | v1.8.0 | Lightning Web Component | findByNumber |  | New | Change set | Jest | Conditional | Not deployed | Only if POC shows global search breaks
113 | Part 8 | v1.8.0 | Lightning Web Component | searchComponent |  | Existing (change) | Change set |  | Conditional | Not deployed | Possibly reuse for Find by number
114 | Part 9 | v1.9.0 | Visualforce Page | 19 customer document pages (BookingForm, letters, quotations, receipts) |  | Existing (change) | Change set |  | Conditional | Not deployed | Keep real number for document teams
115 | Part 9 | v1.9.0 | Aura Component | createBookingCmp |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked display
116 | Part 9 | v1.9.0 | Aura Component | siteVisitFeedbackForm |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked display
117 | Part 9 | v1.9.0 | Lightning Web Component | cancellationRequest |  | Existing (change) | Change set |  | Conditional | Not deployed | Fails completely if Opportunity Mobile__c is hidden
118 | Part 9 | v1.9.0 | Lightning Web Component | kycAndQuotationTabComponent |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked co-applicant entry
119 | Part 9 | v1.9.0 | Lightning Web Component | opportunitySummaryLWC |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked display
120 | Part 9 | v1.9.0 | Lightning Web Component | registrationTeamFileUpload |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked display
121 | Part 9 | v1.9.0 | Lightning Web Component | showConvertedOppRecord |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked display
122 | Part 9 | v1.9.0 | Quick Action | Contact.Co_Applicant_1 / 2 / 3, Contact.Update_Contact_Details |  | Existing (change) | Change set |  | Conditional | Not deployed | Masked entry
123 | Part 11 | v2.0.0 | Lightning Page | Lead_Record_Page |  | Existing (change) | Change set |  | Yes | Not deployed | Add maskedPhonePanel (click-to-dial on)
124 | Part 11 | v2.0.0 | Lightning Page | Lead_Record_Page3 |  | Existing (change) | Change set |  | Yes | Not deployed | Add maskedPhonePanel (click-to-dial on)
125 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page |  | Existing (change) | Change set |  | Yes | Not deployed | Swap phone fields for entry fields
126 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page |  | Existing (change) | Change set |  | Yes | Not deployed | Add maskedPhonePanel (click-to-dial on)
127 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page1_sales |  | Existing (change) | Change set |  | Yes | Not deployed | Swap phone fields for entry fields
128 | Part 11 | v2.0.0 | Lightning Page | New_Lead_Page1_sales |  | Existing (change) | Change set |  | Yes | Not deployed | Add maskedPhonePanel (click-to-dial on)
129 | Part 11 | v2.0.0 | Lightning Page | Sales_Lead_Record_Page |  | Existing (change) | Change set |  | Yes | Not deployed | Add maskedPhonePanel (click-to-dial on)
130 | Part 11 | v2.0.0 | Permission Set | Phone_Number_Full_Access |  | New | Change set |  | Yes | Not deployed | Assign to integration users
131 | Part 11 | v2.0.0 | Profile | ~40 rep profiles (Presales outbound, Sales, CRM Team, Referral Team, TLs ...) |  | Existing (change) | Manual / Change set |  | Yes | Not deployed | Remove phone-field access; Export Reports / API Enabled where safe
132 | Part 11 | v2.0.0 | Lightning App (assignment) | Pre_Sales (Gsquare Housing) |  | Existing (change) | Manual / Change set |  | Pilot cleanup | Not deployed | Remove POC assignment row
133 | Security fix | optional | Named Credential | MCube_API |  | New | Change set |  | Yes (optional) | Not deployed | Separate approval
134 | Security fix | optional | Apex Class | McubeAutoDailerApi |  | Existing (change) | Change set |  | Yes (optional) | Not deployed | Use Named Credential MCube_API instead of hard-coded token / http URL
135 | Security fix | optional | Apex Class | mCubeController |  | Existing (change) | Change set |  | Yes (optional) | Not deployed | Use Named Credential MCube_API instead of hard-coded token / http URL
136 | Security fix | optional | Apex Class | McubeSoftphoneAddOnController |  | Existing (change) | Change set |  | Yes (optional) | Not deployed | Use Named Credential MCube_API instead of hard-coded token / http URL
137 | Part 1 |  | Manual step | M1 |  | Manual | Manual |  | Yes | Not deployed | Assign permission set Phone Access Audit Viewer to admins who review audits
138 | Part 2 |  | Manual step | M2 |  | Manual | Manual |  | Pilot only (decide) | Not deployed | Clone profile Presales outbound -> POC Masked Rep
139 | Part 2 |  | Manual step | M3 |  | Manual | Manual |  | Pilot only | Not deployed | Activate Sales_Lead_Record_Page_Masked_POC for Gsquare Housing / Desktop / Pre Sales / POC Masked Rep
140 | Part 6 |  | Manual step | M9 |  | Manual | Manual |  | Yes | Not deployed | Schedule PhoneAuditPurgeBatch nightly
141 | Part 6 |  | Manual step | M10 |  | Manual | Manual |  | Yes | Not deployed | Assign Phone_Number_Reveal to TLs, Heads, Admins
142 | Part 11 |  | Manual step | M11 |  | Manual | Manual |  | Yes | Not deployed | Assign Phone_Number_Full_Access to integration users (MCube, Yotel, Zetta, website/portal, SlashRTC log user)
143 | Part 11 |  | Manual step | M12 |  | Manual | Manual |  | Yes | Not deployed | Activate pages / assignments that cannot be deployed (Pre_Sales app)
144 | Part 13 |  | Manual step | M13 |  | Manual | Manual |  | Yes | Not deployed | Production: Validate change set with Run specified tests, then Quick Deploy

## Manual Steps
Manual Steps (cannot be deployed)
Do these in Setup at the right point of each part
Step | Part | What to do | Where | Sandbox status | Needed in Production
M1 | Part 1 | Assign permission set Phone Access Audit Viewer to admins who review audits | Setup > Permission Sets | Not done | Yes
M2 | Part 2 | Clone profile Presales outbound -> POC Masked Rep | Setup > Profiles > Clone | Done | Pilot only (decide)
M3 | Part 2 | Activate Sales_Lead_Record_Page_Masked_POC for Gsquare Housing / Desktop / Pre Sales / POC Masked Rep | Lightning App Builder > Activation | Done | Pilot only
M4 | Part 2 | Create test users POC MCube Rep, POC SlashRTC Rep | Setup > Users | Done | No
M5 | Part 2 | Create Pre Sales test Leads owned by each test user (tester or dummy numbers) | Leads | Not done | No
M6 | Part 3 | Set POC MCube Rep MobilePhone = agent number registered with MCube | Setup > Users | Not done | No
M7 | Part 3 | SlashRTC agent exists for POC SlashRTC Rep email (tptUniqueId = user email); sandbox origin allowed by SlashRTC | SlashRTC admin / vendor | Not done | No
M8 | Part 3 | SlashRTC call center CTI Adapter URL -> /apex/index (sandbox only, done manually by you) | Setup > Call Centers > SlashRTC Call Center Adapter > Edit | Manual - pending | No
M9 | Part 6 | Schedule PhoneAuditPurgeBatch nightly | Setup > Apex Classes > Schedule Apex | Not started | Yes
M10 | Part 6 | Assign Phone_Number_Reveal to TLs, Heads, Admins | Setup > Permission Sets | Not started | Yes
M11 | Part 11 | Assign Phone_Number_Full_Access to integration users (MCube, Yotel, Zetta, website/portal, SlashRTC log user) | Setup > Permission Sets | Not started | Yes
M12 | Part 11 | Activate pages / assignments that cannot be deployed (Pre_Sales app) | Lightning App Builder | Not started | Yes
M13 | Part 13 | Production: Validate change set with Run specified tests, then Quick Deploy | Setup > Inbound Change Sets | Not started | Yes

## Test Classes
Test Classes and Coverage
Target above 85% per class, never SeeAllData
Test class | Covers | Part | Tests | Coverage (sandbox) | Status
PhoneMaskUtilTest | PhoneMaskUtil | Part 1 | 12 | 100% | Deployed (Sandbox)
PhoneMaskingConfigTest | PhoneMaskingConfig | Part 1 | 6 | 98.2% | Deployed (Sandbox)
MaskedDialServiceTest | MaskedDialService | Part 1 | 18 | 100% | Deployed (Sandbox)
MaskedDialServiceCTITest | MaskedDialServiceCTI | Part 1 | 6 | 93.5% | Deployed (Sandbox)
PhoneTestDataFactory | (test data utility) | Part 1 | - | - | Deployed (Sandbox)
MaskedPhonePanelControllerTest | MaskedPhonePanelController | Part 2 | 11 | 100% | Deployed (Sandbox)
McubeMaskedClickToCallTest + McubeSoftphoneAddOnControllerTest | McubeSoftphoneAddOnController | Part 3 | - | 87.9% | Deployed (Sandbox)
MaskedDialServiceTest (v1.3.0, +5) | MaskedDialService | Part 3 | 23 | 100% | Deployed (Sandbox)
MaskedDialServiceCTITest (v1.3.0, +3) | MaskedDialServiceCTI | Part 3 | 9 | 94.4% | Deployed (Sandbox)
LeadPhoneEntryHandlerTest (+ LeadTriggerTest, LeadTriggerHandlerTest) | LeadPhoneEntryHandler, LeadTrigger | Part 4 | 20 | Handler 100% Â· LeadTrigger 80.1% | Deployed (Sandbox)
(existing test classes of Part 5 components) | Part 5 changed classes | Part 5 |  | keep >= current | Planned
PhoneRevealServiceTest | PhoneRevealService | Part 6 |  | target > 85% | Planned
PhoneAuditPurgeBatchTest | PhoneAuditPurgeBatch | Part 6 |  | target > 85% | Planned
FreeTextMaskServiceTest | FreeTextMaskService, FeedItemPhoneMaskTrigger | Part 7 |  | target > 85% | Planned
FindByNumberControllerTest | FindByNumberController | Part 8 |  | target > 85% | Conditional

## Backups
Backups of Original Code
Taken before any existing component changes
Backup | Contents | Location | Retrieved | Git commit | Status
Baseline v1.0.0 | 528 files: 44 Apex, LeadTrigger, 12 Aura, 11 LWC, 21 VF, 4 Lightning pages, 4 quick actions, 3 flows, 3 call centers, 38 phone fields, 167 profiles, 47 permission sets | force-app (git tag v1.0.0) | 2026-10-03 | 9a87598 | Backed up
Pre_Sales app snapshot | Gsquare Housing app before the POC row | force-app/main/default/applications (commit 1adf63f) | 2026-10-05 | 1adf63f | Backed up
Part 3 pre-change backup | mcubeSoftphoneCTIAddOn, McubeSoftphoneAddOnController (+Test), index, slashPhone, slashPhoneApp, leadOp (+Test), 3 call centers | backup/v1.3.0-pre-change (with SHA256SUMS) | 2026-10-06 | f2c7e4f | Backed up
Part 4 pre-change backup | LeadTrigger, NewLeadCmp, NewRefLeadCmp, RelatedSourceHandler, LeadTriggerHandler (+tests), New_Lead_Page, New_Lead_Page1_sales (changed since baseline: +8 lines tab display), Lead.New_Referral_Lead | backup/v1.4.0-pre-change (with SHA256SUMS) | 2026-10-06 | 9b32c8c | Backed up
Part 5a pre-change backup | MakeCall + MakeCallController (+Test), OfflineCallAppAPI (+Test), utilityCallComponent, offlineCallQuickActionCmp, CallPanel, CallPanel_Outbound - identical to baseline | backup/v1.5.0-part5a-pre-change (with SHA256SUMS) | 2026-10-06 | 3c0330b | Backed up
Before Part 7 | TaskTrigger, CallDetailTrigger and handlers (not in baseline) | backup/v1.7.0-pre-change |  |  | Planned
Before Part 11 | All rep profiles, Lead_Record_Page3 | backup/v2.0.0-pre-change |  |  | Planned

## Part 3 Plan
Part 3 (v1.3.0) - Dialer adapters, POC
Explained before implementation; nothing changed yet
New / Existing | Type | Component | Change | Effect for users | Risk
New | Apex test class | McubeMaskedClickToCallTest | Tests the new MCube method: masked click resolves the real number on the server and places the call (MCube callout mocked); denied / no-access / blank cases | None (tests only) | None
Existing | Apex Class | McubeSoftphoneAddOnController | ADD one method clickToCallMasked(recordId, fieldKey): MaskedDialService.resolveOne -> existing clickToCallRemote(recordId, realNumber). Existing methods not edited. | POC MCube user can call from the masked panel; the real number never reaches the browser | Low: additive only
Existing | Visualforce Page | mcubeSoftphoneCTIAddOn | In the onClickToDial listener: IF the click carries fieldKey (masked panel) -> call clickToCallMasked; ELSE existing code unchanged | Normal Phone__c clicks behave exactly as today | Low: one branch
Existing | Aura Component | slashPhone (slashPhoneHelper.js) | In the onClickToDial listener: IF masked click -> runApex MaskedDialServiceCTI.resolveForDial(recordId, fieldKey), replace the number, then run the existing flow (leadOp lookup + postMessage to SlashRTC iframe) | POC SlashRTC user can call from the panel. Real number exists briefly inside the SlashRTC softphone (vendor limitation) | Medium: SlashRTC must accept sandbox origin
Existing (sandbox only) | Call Center | SlashRTCAdapter | Adapter URL -> sandbox index page | SlashRTC softphone in sandbox loads the sandbox page | None in production
New (update) | Profile | POC Masked Rep | Add class access MaskedDialServiceCTI | SlashRTC runApex allowed for POC users | None
New (update) | Lightning Page | Sales_Lead_Record_Page_Masked_POC | Panel property Enable click-to-dial = true | Masked numbers become clickable for POC users | None for other users
Data | User | POC MCube Rep | MobilePhone = agent number registered with MCube | MCube can ring the agent | None
No change | Apex Class | leadOp | None: returns record Ids only (earlier plan corrected) | - | -
No change | Visualforce Page | index | None: screen pop uses recordId | - | -
Not in POC | Managed package | 360CTI (186 users) | Vendor change required | - | Vendor dependency

## Release Bundle
Production Release Bundle - built components (Parts 1-5d)
Every file in release/prod, converted from the sandbox-tested source. Checksums in release/prod/SHA256SUMS. Rebuild: bash scripts/release/build-prod-release.sh
Deploy order | Bundle folder | Part | Version | Metadata Type | Component | File path | SHA-256 (first 12) | For | Tested in sandbox | Prod Status
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | MaskedDialService | release/prod/part1-foundations/classes/MaskedDialService.cls | a8c2c5dc228b | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | MaskedDialService | release/prod/part1-foundations/classes/MaskedDialService.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | MaskedDialServiceCTI | release/prod/part1-foundations/classes/MaskedDialServiceCTI.cls | c5bedd971363 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | MaskedDialServiceCTI | release/prod/part1-foundations/classes/MaskedDialServiceCTI.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | PhoneMaskingConfig | release/prod/part1-foundations/classes/PhoneMaskingConfig.cls | 35b3fcb96581 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | PhoneMaskingConfig | release/prod/part1-foundations/classes/PhoneMaskingConfig.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | PhoneMaskUtil | release/prod/part1-foundations/classes/PhoneMaskUtil.cls | ea923f1f15bc | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class | PhoneMaskUtil | release/prod/part1-foundations/classes/PhoneMaskUtil.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceCTITest | release/prod/part1-foundations/classes/MaskedDialServiceCTITest.cls | 2de826792691 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceCTITest | release/prod/part1-foundations/classes/MaskedDialServiceCTITest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceTest | release/prod/part1-foundations/classes/MaskedDialServiceTest.cls | be47f9305354 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | MaskedDialServiceTest | release/prod/part1-foundations/classes/MaskedDialServiceTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskingConfigTest | release/prod/part1-foundations/classes/PhoneMaskingConfigTest.cls | df947c8de87b | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskingConfigTest | release/prod/part1-foundations/classes/PhoneMaskingConfigTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskUtilTest | release/prod/part1-foundations/classes/PhoneMaskUtilTest.cls | c86517eb7fc7 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | PhoneMaskUtilTest | release/prod/part1-foundations/classes/PhoneMaskUtilTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | PhoneTestDataFactory | release/prod/part1-foundations/classes/PhoneTestDataFactory.cls | 838c454f7ee5 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Apex Class (test) | PhoneTestDataFactory | release/prod/part1-foundations/classes/PhoneTestDataFactory.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Metadata Record | Masked_Phone_Field.Lead_Phone | release/prod/part1-foundations/customMetadata/Masked_Phone_Field.Lead_Phone.md | eb3602e65c12 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Metadata Record | Masked_Phone_Field.Lead_Secondary_Phone | release/prod/part1-foundations/customMetadata/Masked_Phone_Field.Lead_Secondary_Phone.md | 19daa00b73c7 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Metadata Record | Phone_Masking_Setting.Default | release/prod/part1-foundations/customMetadata/Phone_Masking_Setting.Default.md | 4f3042be143f | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Object / Custom Metadata Type (with fields) | Masked_Phone_Field__mdt | release/prod/part1-foundations/objects/Masked_Phone_Field__mdt.object | 669f98730825 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Object / Custom Metadata Type (with fields) | Phone_Access_Audit__c | release/prod/part1-foundations/objects/Phone_Access_Audit__c.object | 1098c11ee9d4 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Object / Custom Metadata Type (with fields) | Phone_Masking_Setting__mdt | release/prod/part1-foundations/objects/Phone_Masking_Setting__mdt.object | e1943db5ee18 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Custom Tab | Phone_Access_Audit__c | release/prod/part1-foundations/tabs/Phone_Access_Audit__c.tab | fc02dd0727e9 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Manifest (package.xml) | package.xml | release/prod/part1-foundations/package.xml | 9514afa794c8 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
1 | part1-foundations | Part 1 | v1.1.0 | Permission Set | Phone_Access_Audit_Viewer | release/prod/part1-foundations/permissionsets/Phone_Access_Audit_Viewer.permissionset | dea06e92ea46 | Production - everyone | Deployed (Sandbox) 0Afft000000LO8zCAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Apex Class | MaskedPhonePanelController | release/prod/part2-panel/classes/MaskedPhonePanelController.cls | 1db09cd4a780 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Apex Class | MaskedPhonePanelController | release/prod/part2-panel/classes/MaskedPhonePanelController.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Apex Class (test) | MaskedPhonePanelControllerTest | release/prod/part2-panel/classes/MaskedPhonePanelControllerTest.cls | 8e22c948bff7 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Apex Class (test) | MaskedPhonePanelControllerTest | release/prod/part2-panel/classes/MaskedPhonePanelControllerTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Lightning Web Component | maskedPhonePanel | release/prod/part2-panel/lwc/maskedPhonePanel/maskedPhonePanel.css | f1df701a3a2c | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Lightning Web Component | maskedPhonePanel | release/prod/part2-panel/lwc/maskedPhonePanel/maskedPhonePanel.html | 2cc369f04123 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Lightning Web Component | maskedPhonePanel | release/prod/part2-panel/lwc/maskedPhonePanel/maskedPhonePanel.js | d44addcdfaf9 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Lightning Web Component | maskedPhonePanel | release/prod/part2-panel/lwc/maskedPhonePanel/maskedPhonePanel.js-meta.xml | 0d33c6f7d7e6 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
2 | part2-panel | Part 2 | v1.2.0 | Manifest (package.xml) | package.xml | release/prod/part2-panel/package.xml | 718673207c21 | Production - everyone | Deployed (Sandbox) 0Afft000000LRq1CAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Apex Class | McubeSoftphoneAddOnController | release/prod/part3-dialers/classes/McubeSoftphoneAddOnController.cls | da6120f267a8 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Apex Class | McubeSoftphoneAddOnController | release/prod/part3-dialers/classes/McubeSoftphoneAddOnController.cls-meta.xml | a242f6e22b47 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Apex Class (test) | McubeMaskedClickToCallTest | release/prod/part3-dialers/classes/McubeMaskedClickToCallTest.cls | f6269ed82086 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Apex Class (test) | McubeMaskedClickToCallTest | release/prod/part3-dialers/classes/McubeMaskedClickToCallTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Aura Component | slashPhone | release/prod/part3-dialers/aura/slashPhone/slashPhone.cmp | 47376363b806 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Aura Component | slashPhone | release/prod/part3-dialers/aura/slashPhone/slashPhone.cmp-meta.xml | 785614510f32 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Aura Component | slashPhone | release/prod/part3-dialers/aura/slashPhone/slashPhone.css | d0da498d01a2 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Aura Component | slashPhone | release/prod/part3-dialers/aura/slashPhone/slashPhoneController.js | 270ad3190442 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Aura Component | slashPhone | release/prod/part3-dialers/aura/slashPhone/slashPhoneHelper.js | 0dd6fb07c512 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Manifest (package.xml) | package.xml | release/prod/part3-dialers/package.xml | 6888e0c79e3e | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Visualforce Page | mcubeSoftphoneCTIAddOn | release/prod/part3-dialers/pages/mcubeSoftphoneCTIAddOn.page | 04cf84ceaff4 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
3 | part3-dialers | Part 3 | v1.3.0 | Visualforce Page | mcubeSoftphoneCTIAddOn | release/prod/part3-dialers/pages/mcubeSoftphoneCTIAddOn.page-meta.xml | b4c9950e6bc4 | Production - everyone | Deployed (Sandbox) 0Afft000000LY6jCAG | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 |  | LeadTrigger.trigger | release/prod/part4-lead-entry/triggers/LeadTrigger.trigger | d76c4f8924ec | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 |  | LeadTrigger.trigger | release/prod/part4-lead-entry/triggers/LeadTrigger.trigger-meta.xml | 7a7f3d2d53ba | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Apex Class | LeadPhoneEntryHandler | release/prod/part4-lead-entry/classes/LeadPhoneEntryHandler.cls | 44394fa359a3 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Apex Class | LeadPhoneEntryHandler | release/prod/part4-lead-entry/classes/LeadPhoneEntryHandler.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Apex Class (test) | LeadPhoneEntryHandlerTest | release/prod/part4-lead-entry/classes/LeadPhoneEntryHandlerTest.cls | ff4bcdf806b0 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Apex Class (test) | LeadPhoneEntryHandlerTest | release/prod/part4-lead-entry/classes/LeadPhoneEntryHandlerTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmp.auradoc | 60705e943572 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmp.cmp | a883464b3486 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmp.cmp-meta.xml | 26bafa2e57d5 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmp.css | e0afee0398c4 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmp.design | 5ff4b67b38f3 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmpController.js | 441aea094a35 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmpHelper.js | f78896d8f5bd | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewLeadCmp | release/prod/part4-lead-entry/aura/NewLeadCmp/NewLeadCmpRenderer.js | 38731048a539 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewRefLeadCmp | release/prod/part4-lead-entry/aura/NewRefLeadCmp/NewRefLeadCmp.cmp | 8dc9a335294b | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewRefLeadCmp | release/prod/part4-lead-entry/aura/NewRefLeadCmp/NewRefLeadCmp.cmp-meta.xml | 3757f400d527 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewRefLeadCmp | release/prod/part4-lead-entry/aura/NewRefLeadCmp/NewRefLeadCmpController.js | 1645bb0df45f | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Aura Component | NewRefLeadCmp | release/prod/part4-lead-entry/aura/NewRefLeadCmp/NewRefLeadCmpHelper.js | f78896d8f5bd | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Custom Object / Custom Metadata Type (with fields) | Lead | release/prod/part4-lead-entry/objects/Lead.object | aafbb3299259 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
4 | part4-lead-entry | Part 4 | v1.4.0 | Manifest (package.xml) | package.xml | release/prod/part4-lead-entry/package.xml | 9451f1667341 | Production - everyone | Deployed (Sandbox) 0Afft000000Lc77CAC | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | MakeCallController | release/prod/part5a-calling/classes/MakeCallController.cls | 2f6c04583ce0 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | MakeCallController | release/prod/part5a-calling/classes/MakeCallController.cls-meta.xml | 8ec13a9efa48 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | MaskedDialService | release/prod/part5a-calling/classes/MaskedDialService.cls | a8c2c5dc228b | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | MaskedDialService | release/prod/part5a-calling/classes/MaskedDialService.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | OfflineCallAppAPI | release/prod/part5a-calling/classes/OfflineCallAppAPI.cls | 962740bbee63 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | OfflineCallAppAPI | release/prod/part5a-calling/classes/OfflineCallAppAPI.cls-meta.xml | 331f43ffe1e3 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | PhoneDisplayService | release/prod/part5a-calling/classes/PhoneDisplayService.cls | 395e19ee99fa | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class | PhoneDisplayService | release/prod/part5a-calling/classes/PhoneDisplayService.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class (test) | PhoneDisplayServiceTest | release/prod/part5a-calling/classes/PhoneDisplayServiceTest.cls | 36dd6f2c7618 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class (test) | PhoneDisplayServiceTest | release/prod/part5a-calling/classes/PhoneDisplayServiceTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class (test) | PhoneMaskingCallScreensTest | release/prod/part5a-calling/classes/PhoneMaskingCallScreensTest.cls | ffa49b5c449a | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Apex Class (test) | PhoneMaskingCallScreensTest | release/prod/part5a-calling/classes/PhoneMaskingCallScreensTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Custom Object / Custom Metadata Type (with fields) | Lead | release/prod/part5a-calling/objects/Lead.object | ec632285f7c0 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
5 | part5a-calling | Part 5 | v1.5.0 (5a) | Manifest (package.xml) | package.xml | release/prod/part5a-calling/package.xml | 3b1ffa635783 | Production - everyone | Deployed (Sandbox) 0Afft000000Lf3NCAS | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class | LeadHistoryandActivityController | release/prod/part5b-history/classes/LeadHistoryandActivityController.cls | 6a02768af710 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class | LeadHistoryandActivityController | release/prod/part5b-history/classes/LeadHistoryandActivityController.cls-meta.xml | 8ec13a9efa48 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class | mCubeController | release/prod/part5b-history/classes/mCubeController.cls | 683ff5c6df61 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class | mCubeController | release/prod/part5b-history/classes/mCubeController.cls-meta.xml | 311ca4a715d6 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class | PhoneDisplayService | release/prod/part5b-history/classes/PhoneDisplayService.cls | 395e19ee99fa | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class | PhoneDisplayService | release/prod/part5b-history/classes/PhoneDisplayService.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class (test) | PhoneMaskingHistoryTest | release/prod/part5b-history/classes/PhoneMaskingHistoryTest.cls | e4cb2b6bc259 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Apex Class (test) | PhoneMaskingHistoryTest | release/prod/part5b-history/classes/PhoneMaskingHistoryTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Custom Object / Custom Metadata Type (with fields) | Call_Detail__c | release/prod/part5b-history/objects/Call_Detail__c.object | 77589815f51d | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
6 | part5b-history | Part 5 | v1.5.0 (5b) | Manifest (package.xml) | package.xml | release/prod/part5b-history/package.xml | b2eb9c547a99 | Production - everyone | Deployed (Sandbox) 0Afft000000LfszCAC | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class | LeadMergeController | release/prod/part5c-lead-tools/classes/LeadMergeController.cls | c0cd2ecb5940 | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class | LeadMergeController | release/prod/part5c-lead-tools/classes/LeadMergeController.cls-meta.xml | 8ec13a9efa48 | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class | PhoneDisplayService | release/prod/part5c-lead-tools/classes/PhoneDisplayService.cls | 395e19ee99fa | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class | PhoneDisplayService | release/prod/part5c-lead-tools/classes/PhoneDisplayService.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class | updateContactDetails | release/prod/part5c-lead-tools/classes/updateContactDetails.cls | 3157a9439853 | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class | updateContactDetails | release/prod/part5c-lead-tools/classes/updateContactDetails.cls-meta.xml | 8ec13a9efa48 | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class (test) | PhoneMaskingLeadToolsTest | release/prod/part5c-lead-tools/classes/PhoneMaskingLeadToolsTest.cls | f277a34f5bbb | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Apex Class (test) | PhoneMaskingLeadToolsTest | release/prod/part5c-lead-tools/classes/PhoneMaskingLeadToolsTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
7 | part5c-lead-tools | Part 5 | v1.5.0 (5c) | Manifest (package.xml) | package.xml | release/prod/part5c-lead-tools/package.xml | 66bd9f007bec | Production - everyone | Deployed (Sandbox) 0Afft000000LkRFCA0 | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Apex Class | LeadBulkPushController | release/prod/part5d-push/classes/LeadBulkPushController.cls | 4b1c5e77618a | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Apex Class | LeadBulkPushController | release/prod/part5d-push/classes/LeadBulkPushController.cls-meta.xml | 356db6109364 | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Apex Class | LeadYotelBulkPushController | release/prod/part5d-push/classes/LeadYotelBulkPushController.cls | 7c576df073ca | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Apex Class | LeadYotelBulkPushController | release/prod/part5d-push/classes/LeadYotelBulkPushController.cls-meta.xml | 356db6109364 | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Apex Class (test) | PhoneMaskingPushTest | release/prod/part5d-push/classes/PhoneMaskingPushTest.cls | 154004ee2ed5 | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Apex Class (test) | PhoneMaskingPushTest | release/prod/part5d-push/classes/PhoneMaskingPushTest.cls-meta.xml | 87b91a7450c6 | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
8 | part5d-push | Part 5 | v1.5.0 (5d) | Manifest (package.xml) | package.xml | release/prod/part5d-push/package.xml | d324f6523942 | Production - everyone | Deployed (Sandbox) 0Afft000000Lm1dCAC | Not deployed
9 | part2-pilot | Part 2 | v1.2.0 | Lightning Page | Sales_Lead_Record_Page_Masked_POC | release/prod/part2-pilot/flexipages/Sales_Lead_Record_Page_Masked_POC.flexipage | 9354cdba5c3c | Production pilot only (clone POC profile first) | Deployed (Sandbox) 0Afft000000LRq1CAG / 0Afft000000LRzhCAG | Not deployed
9 | part2-pilot | Part 2 | v1.2.0 | Manifest (package.xml) | package.xml | release/prod/part2-pilot/package.xml | b158c134f515 | Production pilot only (clone POC profile first) | Deployed (Sandbox) 0Afft000000LRq1CAG / 0Afft000000LRzhCAG | Not deployed
9 | part2-pilot | Part 2 | v1.2.0 | Profile | POC Masked Rep | release/prod/part2-pilot/profiles/POC Masked Rep.profile | df1ecd8c7bec | Production pilot only (clone POC profile first) | Deployed (Sandbox) 0Afft000000LRq1CAG / 0Afft000000LRzhCAG | Not deployed

## Release Steps
Production Deploy Steps (Parts 1-5d)
Validate first, then quick deploy. Replace <prod> with the production org alias.
Step | Bundle | What | Command / Where | Prod Status
1 | part1-foundations | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part1-foundations --test-level RunSpecifiedTests --tests PhoneMaskingConfigTest --tests PhoneMaskUtilTest --tests MaskedDialServiceTest --tests MaskedDialServiceCTITest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
2 | part2-panel | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part2-panel --test-level RunSpecifiedTests --tests MaskedPhonePanelControllerTest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
3 | part2-pilot | Pilot only: clone Presales outbound -> POC Masked Rep in Setup, then deploy | sf project deploy start --metadata-dir release/prod/part2-pilot --test-level NoTestRun | --target-org <prod>
3b | part3-dialers | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part3-dialers --test-level RunSpecifiedTests --tests McubeMaskedClickToCallTest --tests McubeSoftphoneAddOnControllerTest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
3c | part4-lead-entry | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part4-lead-entry --test-level RunSpecifiedTests --tests LeadPhoneEntryHandlerTest --tests LeadTriggerTest --tests LeadTriggerHandlerTest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
3d | part5a-calling | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part5a-calling --test-level RunSpecifiedTests --tests PhoneDisplayServiceTest --tests PhoneMaskingCallScreensTest --tests MakeCallControllerTest --tests OfflineCallAppAPITest --tests MaskedDialServiceTest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
3e | part5b-history | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part5b-history --test-level RunSpecifiedTests --tests PhoneMaskingHistoryTest --tests PhoneDisplayServiceTest --tests mCubeController_Test --tests mCubeControllerTestExtended --tests LeadHistoryandActivityControllerTest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
3f | part5c-lead-tools | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part5c-lead-tools --test-level RunSpecifiedTests --tests PhoneMaskingLeadToolsTest --tests PhoneDisplayServiceTest --tests LeadMergeControllerTest (not updateContactDetailsTest - fails before 5c, D3) | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
3g | part5d-push | Validate in production, then quick deploy | sf project deploy validate --metadata-dir release/prod/part5d-push --test-level RunSpecifiedTests --tests PhoneMaskingPushTest --tests LeadBulkPushControllerTest --tests LeadYotelBulkPushControllerTest | --target-org <prod> then sf project deploy quick --job-id <id> --target-org <prod>
4 | (manual) | Assign Phone Access Audit Viewer to admins | Setup > Permission Sets | Not deployed
5 | (manual, pilot) | Activate masked POC page: Gsquare Housing / Desktop / Pre Sales / POC Masked Rep | Lightning App Builder > Activation | Not deployed
6 | (check) | Run scripts/apex/v1.1.0-1 and -2 (read-only) | Developer Console > Execute Anonymous | Not deployed

## Part 4 Plan
Part 4 (v1.4.0) - Lead creation with hidden numbers
Explained before implementation; originals backed up in backup/v1.4.0-pre-change
New / Existing | Type | Component | Change | Effect for users | Risk
New | Custom Field (Phone) | Lead.Phone_Entry__c | Label "Phone". Reps type the primary number here when creating a Lead. Always empty after save. | Masked reps can create Leads | None
New | Custom Field (Phone) | Lead.Secondary_Phone_Entry__c | Label "Secondary Phone". Add / change the secondary number. Always empty after save. | Masked reps can add or change the secondary number | None
New | Apex Class | LeadPhoneEntryHandler | Before insert / update: copies entry -> Phone__c / Secondary_Phone__c and clears the entry fields. Primary is locked once set (error if an entry value tries to change it). Bulk-safe, no SOQL / DML. | Numbers are saved in the real (hidden) fields exactly as today | Low
New | Apex Class (test) | LeadPhoneEntryHandlerTest | Insert, update, lock, secondary change, blank, 200-record bulk, runAs masked user; > 85%, no SeeAllData | - | -
Existing | Apex Trigger | LeadTrigger | Add ONE call at the very top (after the bypass check): LeadPhoneEntryHandler.beforeSave(...) for before insert / update. Everything else unchanged. | Formatting, duplicate check, round robin and validation rules all see the copied number as today | Medium: LeadTrigger runs for every Lead save; covered by existing LeadTrigger tests + new tests
Existing | Aura Component | NewLeadCmp (Lead New button, desktop + mobile) | In the existing onload step: if the form did not receive Phone__c (user cannot see it), show the entry inputs (required Phone + Secondary Phone) instead. | Users who can see Phone__c: no change. Masked users: same form, entry inputs. | Low
Existing | Aura Component | NewRefLeadCmp (New Referral Lead quick action) | Same as NewLeadCmp | Same | Low
New (update) | Profile | POC Masked Rep | Edit access to the 2 entry fields | POC users can type numbers | None
New (update) | Lightning Page | Sales_Lead_Record_Page_Masked_POC | Add "Secondary Phone" entry field to the details so POC users can add / change the secondary number | POC users only | None
No change | Apex | RelatedSourceHandler, LeadTriggerHandler | Existing formatting + duplicate check keep working on Phone__c | - | -
Deferred to Part 11 | Lightning Page | New_Lead_Page, New_Lead_Page1_sales | Phone fields swapped for panel + entry field at go-live | No change now | -
Unaffected | Integrations | Website / portals / MCube / LeadCreationAPI | Still write Phone__c directly; entry fields not used | No change | -

## Part 5a Plan
Part 5a (v1.5.0) - Calling screens
Explained before implementation; originals in backup/v1.5.0-part5a-pre-change
New / Existing | Type | Component | Change | Effect for users | Risk
New | Apex Class | PhoneDisplayService (+ PhoneDisplayServiceTest) | isMaskedUser(): true when the user cannot read Lead.Phone__c. maskForDisplay(): "+91 9876543221" -> "+91 98XXXXXX21". resolve(recordId, maskedValue, candidates): finds the real number on the server (with sharing) and writes an audit row. | Same masking rule on every screen | Low
New | Custom Field (formula) | Lead.Phone_Masked__c | LEFT 2 + X + RIGHT 2 of Phone__c | Masked number on the call panels | None
Updated (ours) | Apex Class | MaskedDialService | + logAccess(): one audit row per MakeCall / G-Talk dial (deferred when a callout follows) | Every masked call is audited | Low
Existing | Apex Class | MakeCallController | readContacts: masked list for masked users (Lead + Related Source numbers). callCustomer: if the number contains X, find the real one on the server, then call MCube exactly as today. | Current users: no change. Masked users: masked list, call still placed. | Low-medium
Existing | Apex Class | OfflineCallAppAPI | getLeadPhone / getOppPhone: masked for masked users. triggerCall: if the number contains X, find the real one on the server before the G-Talk callout. | Same | Low-medium
Existing | Aura Component | CallPanel, CallPanel_Outbound | Show Phone_Masked__c instead of the blank Phone__c for masked users (detected on load). | Masked users see 98XXXXXX21 instead of an empty line | Low
No change | Aura / LWC | MakeCall, utilityCallComponent, offlineCallQuickActionCmp | They display what Apex returns and send it back; Apex now handles masked values. | - | -
Note | LWC | offlineCallQuickActionCmp | Existing issue found (not changed): treats the getLeadPhone result (a map) as a text number and shows a debug alert. | Report to the owner of this component | -

## Part 5b Plan
Part 5b (v1.5.0) - Call history and logs
Explained before implementation; originals in backup/v1.5.0-part5b-pre-change
New / Existing | Type | Component | Change | Effect for users | Risk
New | Custom Field (formula) | Call_Detail__c.Call_To_Masked__c | Masked customer number of a call (first 2 + last 2) | Masked column for call list views / reports (used at go-live) | None
New | Apex Class (test) | PhoneMaskingHistoryTest | Tests the masked paths of callRecords, GetData and the log masking (callouts mocked) | - | -
Existing | Apex Class | mCubeController.callRecords | For masked users, mask Call_From__c / Call_To__c on the returned call list (in memory, never saved) | Call history list (mCubeLightningPage) shows 98XXXXXX21 for masked users; unchanged for others | Low
Existing | Apex Class | mCubeController.makeCall / makeCallZetta (log__c) | Wrap the 3 Request__c and 2 Response__c values in PhoneMaskUtil.maskInText - numbers in the MCube logs are masked for everyone | Admins reading log__c see masked numbers (by design); MCube calls unchanged | Low
Existing | Apex Class | LeadHistoryandActivityController.GetData | For masked users: mask OldValue / NewValue of phone-field history rows (Phone__c, Secondary_Phone__c are history-tracked) and callfrom / callto | History screen shows masked old / new numbers for masked users; unchanged for others | Low
No change | Aura | mCubeLightningPage, LeadHistoryandActivityCmp | They display what Apex returns | - | -
Later | Free text | Task Subject / Description in the history | Numbers typed in notes are handled by Part 7 (free-text masking) | - | -

## Part 5c Plan
Part 5c (v1.5.0) - Lead Merge and Update Contact Details
Explained before implementation; originals in backup/v1.5.0-part5c-pre-change
New / Existing | Type | Component | Change | Effect for users | Risk
Updated (ours) | Apex Class | PhoneDisplayService | + maskRecords(records, fields): masks phone fields on a result list for masked users (in memory only). + prepareContactInput(recordId, phone, secondaryPhone): a masked value sent back by a screen is replaced by the stored number (never saved masked); for masked users the primary stays locked once set. | Same rules as Parts 4 / 5a | Low
New | Apex Class (test) | PhoneMaskingLeadToolsTest | Merge lists masked / unchanged; Update Contact: masked values never saved, secondary change saved, primary change refused for masked users, unmasked users unchanged | - | -
Existing | Apex Class | LeadMergeController | getLeads / getSearchLeads: phone numbers in the results masked for masked users (2 return lines become assign + mask + return). mergeLead unchanged. | Merge screen shows 98XXXXXX21 for masked users; merge works as before | Low
Existing | Apex Class | updateContactDetails | getcontactdetails: +1 line (mask for masked users). savecontactdetails: +5 lines at the top (prepareContactInput) - masked values restored to the stored numbers, primary locked for masked users. | Masked users: see masked, can change secondary + emails; a masked value is never written back. Others: unchanged. | Medium (writes data) - covered by new + existing tests
No change | Aura | LeadMergeCmp, UpdateContactDetails | Screens show what Apex returns; the phone inputs have no format check, so masked values pass validation | - | -
Existing issue (not changed) | Apex Class | LeadMergeController.getLeads | Returns every Lead except the current one with no limit, and the class has no sharing keyword | Report to the owner; out of scope | -

## Part 5d Plan
Part 5d (v1.5.0) - Bulk push and Yotel push
Explained before implementation; originals in backup/v1.5.0-part5d-pre-change
New / Existing | Type | Component | Change | Effect for users | Risk
Existing | Apex Class | LeadBulkPushController.getSelectedLeads | w.mobileNumber = PhoneDisplayService.forDisplay(l.MobilePhone) - 1 line | Masked users: masked in the data sent to the screen (Bulk push does not display it). Others: unchanged | Low
Existing | Apex Class | LeadYotelBulkPushController.getSelectedLeads | w.mobileNumber = PhoneDisplayService.forDisplay(l.Phone__c) - 1 line; eligibility still computed from the real number; the debug line logs the masked number | Masked users: Yotel selection table shows 98XXXXXX21. Others: unchanged | Low
No change | Apex | pushBulkToDialer, pushBulkToYotel | Receive Lead Ids only and read the real numbers on the server - vendors still get real numbers | - | -
No change | LWC / Aura / VF | leadBulkPush, leadYotelPush, wrappers, apps, BulkLeadPUSHpage, BulkLeadPushYotel | Display what Apex returns | - | -
New | Apex Class (test) | PhoneMaskingPushTest | Selection lists masked for masked users, unchanged for others; eligibility unchanged | - | -
Not in scope | Apex | getUserPicklistValues, rmMobileNumber | Agent / user numbers, not customer numbers | - | -

## Part 5e Plan
Part 5e (v1.5.0) - WhatsApp chat
Explained before implementation; originals in backup/v1.5.0-part5e-pre-change
New / Existing | Type | Component | Change | Effect for users | Risk
Existing | Apex Class | LeadMsgConversationController.getConversationViaConnectApi | Before returning the conversation: for masked users, mask numbers inside message, rawJson and senderName (PhoneMaskUtil.maskInText) - one call to a new @TestVisible helper | Masked users: chat shows the same messages with any phone number masked; the raw data never carries the WhatsApp number. Others: unchanged | Low
No change | Apex | getMessagingSessionId, getTransferContext, transferMessagingSession, getSessionAttachments | Use Full_phone_number__c on the server only; return Ids, status, files - no number | - | -
No change | LWC | leadMsgConversationLWC | Displays what Apex returns | - | -
New | Apex Class (test) | PhoneMaskingWhatsAppTest | Conversation rows masked for masked users, unchanged for others (Connect API not called - helper tested directly) | - | -
Go-live decision (D4) | Standard objects | MessagingEndUser / MessagingSession | Presales outbound has View All on both; the WhatsApp customer record shows the number in standard screens, reports, search. Needs a go-live decision (remove View All / restrict) without breaking chat for reps | Not changed in 5e | Decision
Later (Part 7) | Apex | notifyLeadStakeholders(messagePreview) | Preview text typed in chat - free-text masking | - | -
Test limit | Data | Sandbox has 0 MessagingEndUser records | The chat cannot be tested on screen in the sandbox (no WhatsApp data copied) | - | -